## Summary
Inventory Availability Flash — Manual Test Catalog
Source: docs/spec/manual_tests/*.md · Suite aligned to SPEC 05 + decisions-log
Total cases: 35
Stage | Must | Should | Total
1 — Mock BC API | 6 | 0 | 6
2 — Inventory Service | 9 | 0 | 9
3 — React Website | 8 | 1 | 9
4 — Local E2E | 2 | 1 | 3
5 — Azure | 7 | 1 | 8
ALL | 32 | 3 | 35
How to use
1. Run cases stage-by-stage after automated npm test is green.
2. On each case row set Result = Pass or Fail; fill Tester, Date, Evidence.
3. Stage sign-off only when every Must case on that stage sheet is Pass.
4. Reviewer decisions in force: ASM-001 formula; ASM-007 = Both; WEB-006 = cache-only refresh.
5. Still OPEN (PO): ASM-002 thresholds, ASM-003 project status — verify against configured defaults.

## All Cases
Case ID | Stage | Priority | Title | Traces | Steps | Expected Result | Notes | Result | Tester | Date | Evidence / Link | Comments
MAN-101 | 1 — Mock BC API | Must | Four /BC/* endpoints validate against docx samples | MOCK-002/010–013, SPEC 01 §6 bullet 1 | 1. GET /BC/GetInventory, /BC/GetPurchaseOrders, /BC/Demand, /BC/GetInventoryByProject/<a real projectNo>. 2. Eyeball each payload against the docx sample: field names, casing (expected_Receipt_Date), value shapes. |  |  | Not Run
MAN-102 | 1 — Mock BC API | Must | Same seed → identical dataset across restarts | MOCK-004, SPEC 01 §6 bullet 2 | 1. Capture GET /BC/GetInventory output. 2. Restart the mock (MOCK_SEED=42). 3. Capture again and diff. |  |  | Not Run
MAN-103 | 1 — Mock BC API | Must | All six MOCK-045 edge cases demonstrably present | MOCK-045(a–f), SPEC 01 §6 bullet 3 | ¦ Edge ¦ How to see it ¦ ¦---¦---¦ ¦ (a) negative netInventory ¦ filter /BC/Demand for netInventory < 0 → ≥ 3 rows ¦ ¦ (b) null locationCode ¦ filter /BC/Demand for locationCode == null → ≥ 2 rows ¦ ¦ (c) name/code mismatch ¦ find the "Grand Rapids"/DET row ¦ ¦ (d) fully-ready project ¦ open the all-green project's /BC/GetInventoryByProject ¦ ¦ (e) flooring-ready/additional-short project ¦ open that project — additional items short ¦ ¦ (f) qoh 0 + demand + covering PO ¦ find the item; cross-check an open PO in /BC/GetPurchaseOrders ¦ |  |  | Not Run
MAN-104 | 1 — Mock BC API | Must | Outage switch flips endpoints 200 ↔ 500 live | MOCK-070/071, SPEC 01 §6 bullet 4 | 1. POST /admin/outage {"enabled": true, "endpoints": ["inventory"]}. 2. GET /BC/GetInventory → 500; GET /BC/Demand → 200. 3. GET /admin/outage reflects state. 4. POST /admin/outage {"enabled": false} → all back to 200. |  |  | Not Run
MAN-105 | 1 — Mock BC API | Must | Demand reconciles with per-project items | MOCK-044, SPEC 01 §6 bullet 5 | 1. List projects via GET /BC/_mock/GetProjects. 2. Sum items across all GetInventoryByProject responses. 3. Compare to GET /BC/Demand. |  |  | Not Run
MAN-106 | 1 — Mock BC API | Must | Mock markers & credential hygiene | MOCK-005, MOCK-060/061 | 1. Confirm X-Mock-Api: true header on responses. 2. Confirm sale headers live under /BC/_mock/GetProjects (non-canonical path). 3. Grep the repo — no source credential anywhere (mirrors TEST-024.5). |  |  | Not Run
MAN-201 | 2 — Inventory Service | Must | /api/inventory hand-verifiable against raw feeds (ASM-001) | SVC-002, ASM-001, SPEC 02 §6 bullet 1 | 1. Pick 3 item+location keys. 2. Pull raw qoh (GetInventory), Σ qpo (GetPurchaseOrders), Σ demand (Demand) for each. 3. Compute expected available = onHand − allocated and availableSqft = available × sqftPerCase. 4. Compare to GET /api/inventory for those rows. |  |  | Not Run
MAN-202 | 2 — Inventory Service | Must | Formula & thresholds are config-driven (PB-001 guardrail) | SVC-002/003, PB-001, SPEC 02 §6 bullet 2 | 1. Note current available/color for a sample row. 2. Change the availability strategy to qoh + onPO − demand and/or a threshold via config (PUT /api/admin/config or config file per implementation). 3. Re-read /api/inventory. |  |  | Not Run
MAN-203 | 2 — Inventory Service | Must | Runtime interval change without restart | SVC-011, TEST-031, SPEC 02 §6 bullet 3 | 1. Observe refresh cadence in logs (default local 60 s). 2. PUT /api/admin/config {"refreshSeconds": 15}. 3. Watch the next cycles. |  |  | Not Run
MAN-204 | 2 — Inventory Service | Must | Outage drill: keep serving last-good (TEST-030) | SVC-014, SVC-031, MOCK-070, TEST-030, SPEC 02 §6 bullet 4 | 1. Note current refreshedAt from /api/status. 2. Enable mock outage (POST /admin/outage {"enabled": true}). 3. Wait for the next refresh cycle. 4. Check logs, /api/status, and /api/inventory. 5. Disable outage; wait one cycle. | - Failed cycle logged; alert sink fires; consecutiveFailures increments. - /api/status shows unhealthy / per-source failed. - /api/inventory still serves the previous snapshot with the OLD refreshedAt (last-good). - After outage off, recovery within one cycle; refreshedAt advances. |  | Not Run
MAN-205 | 2 — Inventory Service | Must | Project-fetch failure returns 503, not stale (TEST-017 live) | SVC-042a, PB-003, SPEC 02 §6 bullet 5 | 1. Enable outage on the project endpoint only (POST /admin/outage {"enabled": true, "endpoints": ["project"]}). 2. GET /api/projects/:projectNo. 3. GET /api/inventory alongside. |  |  | Not Run
MAN-206 | 2 — Inventory Service | Must | Readers never see a partial refresh | SVC-021, SPEC 02 §6 bullet 6 | 1. Hammer GET /api/inventory in a loop during an active refresh cycle (e.g. while true; do curl -s .../api/inventory ¦ jq '.refreshedAt'; done). |  |  | Not Run
MAN-207 | 2 — Inventory Service | Must | Project endpoint splits flooring/additional + ASM-003 statuses | SVC-042, ASM-003, MOCK-045(d)(e), SPEC 02 §6 bullet 7 | 1. GET /api/projects/<all-green project> (MOCK-045d). 2. GET /api/projects/<flooring-ready/additional-short project> (MOCK-045e). |  |  | Not Run
MAN-208 | 2 — Inventory Service | Must | Admin endpoints reject unauthenticated mutation (guard on) | SVC-045, PB-007, SPEC 02 §6 bullet 8 | 1. Run the service with the production guard enabled. 2. PUT /api/admin/config and POST /api/admin/refresh without X-Admin-Token. 3. Retry with the token. |  |  | Not Run
MAN-209 | 2 — Inventory Service | Must | Invariant: no middleware URL/credential leaks to any /api response | SVC-044, SPEC 00 §3 invariant | 1. Scan every /api/* response body/headers for BC_BASE_URL, BC_AUTH_TOKEN, or the mock host. |  |  | Not Run
MAN-301 | 3 — React Website | Must | Satellite screen parity (screenshot 1) | WEB-020…030, TEST-032, SPEC 03 §6 bullet 1 | 1. Open Satellites; select a satellite (e.g. Detroit). 2. Compare against screenshot 1. | - Sidebar Inventory Filters: Satellite / Item Category / Item dropdowns + Clear filters. - Main title "All Inventory Items"; grid grouped by Item Category (FLOORING block collapsible). - Columns in order: Item Category, Item, On Hand, Allocated, Available, Available (ft²), Ordered. - Available / Available (ft²) cells colored green/yellow/red per ASM-002. - Numbers right-aligned, ft² 2-decimals, thousands separators. |  | Not Run
MAN-302 | 3 — React Website | Must | Project screen parity (screenshot 2) | WEB-040…050, TEST-032, SPEC 03 §6 bullet 2 | 1. Open Projects; select the MOCK-045(e) project (flooring ready / additional short). | - Sale Selection panel: Sale #, Satellite, Customer, BC Status, File Status, Install Date (Install Date in red). - Inventory Status panel: Flooring Materials / Additional Materials rows with status dots. - Gold warning callout visible (additional not available) — hidden on an all-green project (MOCK-045d). - Two captioned tables (Flooring, Additional Materials), columns: Product, Item Category, Required, Available, Ordered, Picked, Remainder, Item Status. - Totals row per table; Picked renders 0.00; Item Status icons per ASM-003. |  | Not Run
MAN-303 | 3 — React Website | Must | Palette audit (exact brand hexes) | WEB-010…014, SPEC 03 §6 bullet 3 | 1. Inspect computed styles for background, text, interactive, warning elements. |  |  | Not Run
MAN-304 | 3 — React Website | Must | Network isolation audit (TEST-033) | WEB-003, TEST-033, SPEC 03 §6 bullet 4 | 1. Open dev-tools Network; clear. 2. Click through both screens, all filters, project switching. |  |  | Not Run
MAN-305 | 3 — React Website | Must | Responsive check | WEB-002, SPEC 03 §6 bullet 5 |  |  |  | Not Run
MAN-306 | 3 — React Website | Must | Refresh icon is cache-only (WEB-006 reviewer decision) ⭐ | WEB-006, decisions-log 2026-07-21, SPEC 03 §6 bullet 6 | 1. Note current "Last Updated" value (it displays refreshedAt from the API envelope). 2. Open dev-tools Network; click the header refresh icon. | - The click re-reads /api/* and refreshes the on-screen data (filters/grids re-fetch). - No POST /api/admin/refresh request appears in the network tab. - The "Last Updated" / refreshedAt value does not change because of this click — it only advances when a service timer cycle completes (SVC-010). If a timer cycle happens to finish in the same moment, that is coincidental, not caused by the icon. |  | Not Run
MAN-307 | 3 — React Website | Must | Inventory Status = shortage board + health widget (ASM-007 = Both) ⭐ | WEB-060…063, ASM-007, SPEC 03 §6 bullet 7 | 1. Open Inventory Status. | - Shortage board (primary): cross-satellite yellow/red rows from /api/inventory (columns: Satellite, Item, On Hand, Allocated, Available, Available (ft²), Ordered, status); filters satellite/category/search; empty state when nothing below threshold. - Health widget (secondary): /api/status panel — overall health, last successful refresh, last attempt, consecutive failures, per-source ok/failed + row counts. - Failure states loud: red banner when healthy:false; gold stale badge when refreshedAt older than 2× interval (WEB-062, ties WEB-005). - refreshSeconds shown with admin control (WEB-063, protected per SVC-045). |  | Not Run
MAN-308 | 3 — React Website | Must | Item Details menu present but disabled; auth gate | WEB-007 (ASM-006), WEB-008 |  |  |  | Not Run
MAN-309 | 3 — React Website | Should | "Last Updated" stale badge behavior | WEB-005 |  |  |  | Not Run
MAN-401 | 4 — Local E2E | Must | End-to-end happy-path + failure flow (TEST-034) | TEST-034, WEB-006, ASM-007, SVC-014 | 1. Filter a satellite on the Satellites screen → confirm grouped, colored grid. 2. Find a shortage item (yellow/red Available). 3. Open a short project (MOCK-045e) → see the two tables + item statuses. 4. See the gold callout ("additional materials not available"). 5. Click the header refresh → confirm cache-only (WEB-006): on-screen data re-fetches from /api/*, no POST /api/admin/refresh in network, "Last Updated" / refreshedAt not force-advanced by the icon. 6. Open Inventory Status → shortage board lists the yellow/red rows and the health widget shows /api/status (ASM-007 = Both). 7. Kill the mock mid-session (or enable full outage) → wait a cycle. 8. Verify stale-but-served: satellite views still render the previous snapshot with the OLD refreshedAt; health widget goes loud (red banner / stale badge); a project fetch now returns 503 (SVC-042a). 9. Restore the mock → recovery within one cycle; refreshedAt advances; banners clear. |  |  | Not Run
MAN-402 | 4 — Local E2E | Must | Definition of Done audit (whole project) | SPEC 05 §5 | - ☐ Every M requirement in specs 01–04 implemented and its acceptance criteria checked (Stages 1–3 sign-offs attached). - ☐ All unit + contract tests green in npm test (link CI run / local output). - ☐ All drills executed with reviewer present or evidence captured (MAN-104, MAN-204, MAN-304, MAN-306, MAN-307, MAN-401; Stage 5: MAN-504 + MAN-508). - ☐ No source credential anywhere in the repo — verified by grep (MOCK-005 / TEST-024.5). - ☐ README documents: run instructions, architecture summary, how to point at real endpoints later (SVC-043 — feeds/project-items only; sale headers replica-only), cost/teardown notes. - ☐ Repo committed with spec suite, code, tests, deploy scripts. |  |  | Not Run
MAN-403 | 4 — Local E2E | Should | Replica-boundary honesty check | SPEC 00 §1/§9, SVC-043, ASM-005 |  |  |  | Not Run
MAN-501 | 5 — Azure | Must | All three apps reachable over HTTPS; web renders live cloud data | AZ-002/005, AZ-012, SPEC 04 §7 bullet 1 |  |  |  | Not Run
MAN-502 | 5 — Azure | Must | Cloud isolation invariant holds | WEB-003, AZ-012, SPEC 04 §7 bullet 2 |  |  |  | Not Run
MAN-503 | 5 — Azure | Must | Key Vault reference resolves; no plaintext secret | AZ-010, AZ-011a, SPEC 04 §7 bullet 3 | 1. Confirm the service starts and reads BC-AUTH-TOKEN / REDIS-URL / ADMIN_TOKEN via Key Vault references + managed identity. 2. Inspect App Service application settings. |  |  | Not Run
MAN-504 | 5 — Azure | Must | Cloud outage drill + alert email (TEST-035 part A) | AZ-040/041/042, SVC-014, MOCK-070, TEST-035, SPEC 04 §7 bullet 4 | 1. Trigger mock outage in cloud (admin route, IP-restricted). 2. Wait for consecutiveFailures ≥ 3. 3. Watch App Insights + the reviewer's inbox. 4. Confirm the site serves the stale snapshot meanwhile. 5. Disable outage → recovery. |  |  | Not Run
MAN-505 | 5 — Azure | Must | Auth branch (DEC-002) | AZ-030/031 |  | - DEC-002a: dev-stub login present, clearly labeled non-production. - DEC-002b: Entra ID Easy Auth on inventory-web gates access; no React code change. |  | Not Run
MAN-506 | 5 — Azure | Must | Teardown leaves zero resources | AZ-001, AZ-062, SPEC 04 §7 bullet 5 |  |  |  | Not Run
MAN-507 | 5 — Azure | Should | Cost matches DEC-001 estimate | DEC-001, AZ-020/021, SPEC 04 §7 bullet 6 |  |  |  | Not Run
MAN-508 | 5 — Azure | Must | Cloud E2E repeat of TEST-034 (TEST-035 part B) ⭐ | TEST-035, TEST-034, WEB-006, ASM-007, SVC-042a, SPEC 04 §7 | 1. Filter a satellite → colored grouped grid. 2. Find a shortage item (yellow/red). 3. Open MOCK-045(e) project → gold callout. 4. Header refresh → cache-only (no POST /api/admin/refresh; refreshedAt not force-advanced). 5. Inventory Status → shortage board and health widget (ASM-007 = Both). 6. Enable mock outage (or stop mock) → wait a cycle → stale-but-served on satellite views; health loud; project fetch 503. 7. Restore → recovery; refreshedAt advances. |  | SPEC 05 TEST-035 requires a cloud repeat of TEST-030 + TEST-034. MAN-504 covers the outage/email half (TEST-030). This case covers the full local E2E half on Azure. | Not Run

## Stage 1
Case ID | Stage | Priority | Title | Traces | Steps | Expected Result | Notes | Result | Tester | Date | Evidence / Link | Comments
MAN-101 | 1 — Mock BC API | Must | Four /BC/* endpoints validate against docx samples | MOCK-002/010–013, SPEC 01 §6 bullet 1 | 1. GET /BC/GetInventory, /BC/GetPurchaseOrders, /BC/Demand, /BC/GetInventoryByProject/<a real projectNo>. 2. Eyeball each payload against the docx sample: field names, casing (expected_Receipt_Date), value shapes. |  |  | Not Run
MAN-102 | 1 — Mock BC API | Must | Same seed → identical dataset across restarts | MOCK-004, SPEC 01 §6 bullet 2 | 1. Capture GET /BC/GetInventory output. 2. Restart the mock (MOCK_SEED=42). 3. Capture again and diff. |  |  | Not Run
MAN-103 | 1 — Mock BC API | Must | All six MOCK-045 edge cases demonstrably present | MOCK-045(a–f), SPEC 01 §6 bullet 3 | ¦ Edge ¦ How to see it ¦ ¦---¦---¦ ¦ (a) negative netInventory ¦ filter /BC/Demand for netInventory < 0 → ≥ 3 rows ¦ ¦ (b) null locationCode ¦ filter /BC/Demand for locationCode == null → ≥ 2 rows ¦ ¦ (c) name/code mismatch ¦ find the "Grand Rapids"/DET row ¦ ¦ (d) fully-ready project ¦ open the all-green project's /BC/GetInventoryByProject ¦ ¦ (e) flooring-ready/additional-short project ¦ open that project — additional items short ¦ ¦ (f) qoh 0 + demand + covering PO ¦ find the item; cross-check an open PO in /BC/GetPurchaseOrders ¦ |  |  | Not Run
MAN-104 | 1 — Mock BC API | Must | Outage switch flips endpoints 200 ↔ 500 live | MOCK-070/071, SPEC 01 §6 bullet 4 | 1. POST /admin/outage {"enabled": true, "endpoints": ["inventory"]}. 2. GET /BC/GetInventory → 500; GET /BC/Demand → 200. 3. GET /admin/outage reflects state. 4. POST /admin/outage {"enabled": false} → all back to 200. |  |  | Not Run
MAN-105 | 1 — Mock BC API | Must | Demand reconciles with per-project items | MOCK-044, SPEC 01 §6 bullet 5 | 1. List projects via GET /BC/_mock/GetProjects. 2. Sum items across all GetInventoryByProject responses. 3. Compare to GET /BC/Demand. |  |  | Not Run
MAN-106 | 1 — Mock BC API | Must | Mock markers & credential hygiene | MOCK-005, MOCK-060/061 | 1. Confirm X-Mock-Api: true header on responses. 2. Confirm sale headers live under /BC/_mock/GetProjects (non-canonical path). 3. Grep the repo — no source credential anywhere (mirrors TEST-024.5). |  |  | Not Run

## Stage 2
Case ID | Stage | Priority | Title | Traces | Steps | Expected Result | Notes | Result | Tester | Date | Evidence / Link | Comments
MAN-201 | 2 — Inventory Service | Must | /api/inventory hand-verifiable against raw feeds (ASM-001) | SVC-002, ASM-001, SPEC 02 §6 bullet 1 | 1. Pick 3 item+location keys. 2. Pull raw qoh (GetInventory), Σ qpo (GetPurchaseOrders), Σ demand (Demand) for each. 3. Compute expected available = onHand − allocated and availableSqft = available × sqftPerCase. 4. Compare to GET /api/inventory for those rows. |  |  | Not Run
MAN-202 | 2 — Inventory Service | Must | Formula & thresholds are config-driven (PB-001 guardrail) | SVC-002/003, PB-001, SPEC 02 §6 bullet 2 | 1. Note current available/color for a sample row. 2. Change the availability strategy to qoh + onPO − demand and/or a threshold via config (PUT /api/admin/config or config file per implementation). 3. Re-read /api/inventory. |  |  | Not Run
MAN-203 | 2 — Inventory Service | Must | Runtime interval change without restart | SVC-011, TEST-031, SPEC 02 §6 bullet 3 | 1. Observe refresh cadence in logs (default local 60 s). 2. PUT /api/admin/config {"refreshSeconds": 15}. 3. Watch the next cycles. |  |  | Not Run
MAN-204 | 2 — Inventory Service | Must | Outage drill: keep serving last-good (TEST-030) | SVC-014, SVC-031, MOCK-070, TEST-030, SPEC 02 §6 bullet 4 | 1. Note current refreshedAt from /api/status. 2. Enable mock outage (POST /admin/outage {"enabled": true}). 3. Wait for the next refresh cycle. 4. Check logs, /api/status, and /api/inventory. 5. Disable outage; wait one cycle. | - Failed cycle logged; alert sink fires; consecutiveFailures increments. - /api/status shows unhealthy / per-source failed. - /api/inventory still serves the previous snapshot with the OLD refreshedAt (last-good). - After outage off, recovery within one cycle; refreshedAt advances. |  | Not Run
MAN-205 | 2 — Inventory Service | Must | Project-fetch failure returns 503, not stale (TEST-017 live) | SVC-042a, PB-003, SPEC 02 §6 bullet 5 | 1. Enable outage on the project endpoint only (POST /admin/outage {"enabled": true, "endpoints": ["project"]}). 2. GET /api/projects/:projectNo. 3. GET /api/inventory alongside. |  |  | Not Run
MAN-206 | 2 — Inventory Service | Must | Readers never see a partial refresh | SVC-021, SPEC 02 §6 bullet 6 | 1. Hammer GET /api/inventory in a loop during an active refresh cycle (e.g. while true; do curl -s .../api/inventory ¦ jq '.refreshedAt'; done). |  |  | Not Run
MAN-207 | 2 — Inventory Service | Must | Project endpoint splits flooring/additional + ASM-003 statuses | SVC-042, ASM-003, MOCK-045(d)(e), SPEC 02 §6 bullet 7 | 1. GET /api/projects/<all-green project> (MOCK-045d). 2. GET /api/projects/<flooring-ready/additional-short project> (MOCK-045e). |  |  | Not Run
MAN-208 | 2 — Inventory Service | Must | Admin endpoints reject unauthenticated mutation (guard on) | SVC-045, PB-007, SPEC 02 §6 bullet 8 | 1. Run the service with the production guard enabled. 2. PUT /api/admin/config and POST /api/admin/refresh without X-Admin-Token. 3. Retry with the token. |  |  | Not Run
MAN-209 | 2 — Inventory Service | Must | Invariant: no middleware URL/credential leaks to any /api response | SVC-044, SPEC 00 §3 invariant | 1. Scan every /api/* response body/headers for BC_BASE_URL, BC_AUTH_TOKEN, or the mock host. |  |  | Not Run

## Stage 3
Case ID | Stage | Priority | Title | Traces | Steps | Expected Result | Notes | Result | Tester | Date | Evidence / Link | Comments
MAN-301 | 3 — React Website | Must | Satellite screen parity (screenshot 1) | WEB-020…030, TEST-032, SPEC 03 §6 bullet 1 | 1. Open Satellites; select a satellite (e.g. Detroit). 2. Compare against screenshot 1. | - Sidebar Inventory Filters: Satellite / Item Category / Item dropdowns + Clear filters. - Main title "All Inventory Items"; grid grouped by Item Category (FLOORING block collapsible). - Columns in order: Item Category, Item, On Hand, Allocated, Available, Available (ft²), Ordered. - Available / Available (ft²) cells colored green/yellow/red per ASM-002. - Numbers right-aligned, ft² 2-decimals, thousands separators. |  | Not Run
MAN-302 | 3 — React Website | Must | Project screen parity (screenshot 2) | WEB-040…050, TEST-032, SPEC 03 §6 bullet 2 | 1. Open Projects; select the MOCK-045(e) project (flooring ready / additional short). | - Sale Selection panel: Sale #, Satellite, Customer, BC Status, File Status, Install Date (Install Date in red). - Inventory Status panel: Flooring Materials / Additional Materials rows with status dots. - Gold warning callout visible (additional not available) — hidden on an all-green project (MOCK-045d). - Two captioned tables (Flooring, Additional Materials), columns: Product, Item Category, Required, Available, Ordered, Picked, Remainder, Item Status. - Totals row per table; Picked renders 0.00; Item Status icons per ASM-003. |  | Not Run
MAN-303 | 3 — React Website | Must | Palette audit (exact brand hexes) | WEB-010…014, SPEC 03 §6 bullet 3 | 1. Inspect computed styles for background, text, interactive, warning elements. |  |  | Not Run
MAN-304 | 3 — React Website | Must | Network isolation audit (TEST-033) | WEB-003, TEST-033, SPEC 03 §6 bullet 4 | 1. Open dev-tools Network; clear. 2. Click through both screens, all filters, project switching. |  |  | Not Run
MAN-305 | 3 — React Website | Must | Responsive check | WEB-002, SPEC 03 §6 bullet 5 |  |  |  | Not Run
MAN-306 | 3 — React Website | Must | Refresh icon is cache-only (WEB-006 reviewer decision) ⭐ | WEB-006, decisions-log 2026-07-21, SPEC 03 §6 bullet 6 | 1. Note current "Last Updated" value (it displays refreshedAt from the API envelope). 2. Open dev-tools Network; click the header refresh icon. | - The click re-reads /api/* and refreshes the on-screen data (filters/grids re-fetch). - No POST /api/admin/refresh request appears in the network tab. - The "Last Updated" / refreshedAt value does not change because of this click — it only advances when a service timer cycle completes (SVC-010). If a timer cycle happens to finish in the same moment, that is coincidental, not caused by the icon. |  | Not Run
MAN-307 | 3 — React Website | Must | Inventory Status = shortage board + health widget (ASM-007 = Both) ⭐ | WEB-060…063, ASM-007, SPEC 03 §6 bullet 7 | 1. Open Inventory Status. | - Shortage board (primary): cross-satellite yellow/red rows from /api/inventory (columns: Satellite, Item, On Hand, Allocated, Available, Available (ft²), Ordered, status); filters satellite/category/search; empty state when nothing below threshold. - Health widget (secondary): /api/status panel — overall health, last successful refresh, last attempt, consecutive failures, per-source ok/failed + row counts. - Failure states loud: red banner when healthy:false; gold stale badge when refreshedAt older than 2× interval (WEB-062, ties WEB-005). - refreshSeconds shown with admin control (WEB-063, protected per SVC-045). |  | Not Run
MAN-308 | 3 — React Website | Must | Item Details menu present but disabled; auth gate | WEB-007 (ASM-006), WEB-008 |  |  |  | Not Run
MAN-309 | 3 — React Website | Should | "Last Updated" stale badge behavior | WEB-005 |  |  |  | Not Run

## Stage 4
Case ID | Stage | Priority | Title | Traces | Steps | Expected Result | Notes | Result | Tester | Date | Evidence / Link | Comments
MAN-401 | 4 — Local E2E | Must | End-to-end happy-path + failure flow (TEST-034) | TEST-034, WEB-006, ASM-007, SVC-014 | 1. Filter a satellite on the Satellites screen → confirm grouped, colored grid. 2. Find a shortage item (yellow/red Available). 3. Open a short project (MOCK-045e) → see the two tables + item statuses. 4. See the gold callout ("additional materials not available"). 5. Click the header refresh → confirm cache-only (WEB-006): on-screen data re-fetches from /api/*, no POST /api/admin/refresh in network, "Last Updated" / refreshedAt not force-advanced by the icon. 6. Open Inventory Status → shortage board lists the yellow/red rows and the health widget shows /api/status (ASM-007 = Both). 7. Kill the mock mid-session (or enable full outage) → wait a cycle. 8. Verify stale-but-served: satellite views still render the previous snapshot with the OLD refreshedAt; health widget goes loud (red banner / stale badge); a project fetch now returns 503 (SVC-042a). 9. Restore the mock → recovery within one cycle; refreshedAt advances; banners clear. |  |  | Not Run
MAN-402 | 4 — Local E2E | Must | Definition of Done audit (whole project) | SPEC 05 §5 | - ☐ Every M requirement in specs 01–04 implemented and its acceptance criteria checked (Stages 1–3 sign-offs attached). - ☐ All unit + contract tests green in npm test (link CI run / local output). - ☐ All drills executed with reviewer present or evidence captured (MAN-104, MAN-204, MAN-304, MAN-306, MAN-307, MAN-401; Stage 5: MAN-504 + MAN-508). - ☐ No source credential anywhere in the repo — verified by grep (MOCK-005 / TEST-024.5). - ☐ README documents: run instructions, architecture summary, how to point at real endpoints later (SVC-043 — feeds/project-items only; sale headers replica-only), cost/teardown notes. - ☐ Repo committed with spec suite, code, tests, deploy scripts. |  |  | Not Run
MAN-403 | 4 — Local E2E | Should | Replica-boundary honesty check | SPEC 00 §1/§9, SVC-043, ASM-005 |  |  |  | Not Run

## Stage 5
Case ID | Stage | Priority | Title | Traces | Steps | Expected Result | Notes | Result | Tester | Date | Evidence / Link | Comments
MAN-501 | 5 — Azure | Must | All three apps reachable over HTTPS; web renders live cloud data | AZ-002/005, AZ-012, SPEC 04 §7 bullet 1 |  |  |  | Not Run
MAN-502 | 5 — Azure | Must | Cloud isolation invariant holds | WEB-003, AZ-012, SPEC 04 §7 bullet 2 |  |  |  | Not Run
MAN-503 | 5 — Azure | Must | Key Vault reference resolves; no plaintext secret | AZ-010, AZ-011a, SPEC 04 §7 bullet 3 | 1. Confirm the service starts and reads BC-AUTH-TOKEN / REDIS-URL / ADMIN_TOKEN via Key Vault references + managed identity. 2. Inspect App Service application settings. |  |  | Not Run
MAN-504 | 5 — Azure | Must | Cloud outage drill + alert email (TEST-035 part A) | AZ-040/041/042, SVC-014, MOCK-070, TEST-035, SPEC 04 §7 bullet 4 | 1. Trigger mock outage in cloud (admin route, IP-restricted). 2. Wait for consecutiveFailures ≥ 3. 3. Watch App Insights + the reviewer's inbox. 4. Confirm the site serves the stale snapshot meanwhile. 5. Disable outage → recovery. |  |  | Not Run
MAN-505 | 5 — Azure | Must | Auth branch (DEC-002) | AZ-030/031 |  | - DEC-002a: dev-stub login present, clearly labeled non-production. - DEC-002b: Entra ID Easy Auth on inventory-web gates access; no React code change. |  | Not Run
MAN-506 | 5 — Azure | Must | Teardown leaves zero resources | AZ-001, AZ-062, SPEC 04 §7 bullet 5 |  |  |  | Not Run
MAN-507 | 5 — Azure | Should | Cost matches DEC-001 estimate | DEC-001, AZ-020/021, SPEC 04 §7 bullet 6 |  |  |  | Not Run
MAN-508 | 5 — Azure | Must | Cloud E2E repeat of TEST-034 (TEST-035 part B) ⭐ | TEST-035, TEST-034, WEB-006, ASM-007, SVC-042a, SPEC 04 §7 | 1. Filter a satellite → colored grouped grid. 2. Find a shortage item (yellow/red). 3. Open MOCK-045(e) project → gold callout. 4. Header refresh → cache-only (no POST /api/admin/refresh; refreshedAt not force-advanced). 5. Inventory Status → shortage board and health widget (ASM-007 = Both). 6. Enable mock outage (or stop mock) → wait a cycle → stale-but-served on satellite views; health loud; project fetch 503. 7. Restore → recovery; refreshedAt advances. |  | SPEC 05 TEST-035 requires a cloud repeat of TEST-030 + TEST-034. MAN-504 covers the outage/email half (TEST-030). This case covers the full local E2E half on Azure. | Not Run